## Backlog
Feature Number | Feature Name | Progress | Version Completed | Notes | BUGS Numbers -->
1 | Create User | 50% | Backend: 1.1.1 Frontend:
2 | User Login | 90% | Backend: 1.1.2 Frontend: | Login functionality seems to be working. No routing logic yet for when a user is logged in. Automated testing needed Need to add logs, and add errors to control logs or whatever I called it
3 | User Logout | 70% | Backend: 1.1.3 Frontend: | Need to add logs, and add errors to control logs or whatever I called it
4 | Delete User | 70% | Backend: 1.1.4 Frontend: | Need to add logs, and add errors to control logs or whatever I called it Possible issues: 1. When an account is deleted, what happens to the group? Could add a fail safe preventing a user from deleting their account if they own a group 2. When an account is deleted, what happens to their posts? Could add a fail safe where if the account can't be found, then the username remains as "unknown user"